## Slide 1
Migrating from
Monolith to Microservices
A Practical Guide for Backend Engineering Teams
Alex Chen
Principal Engineer, Platform Team
March 2026

## Slide 2
The Monolith Today
Why we need to change
D
Deployment Bottleneck
Single deployable = 4-hour release windows
All 20 engineers blocked on one pipeline
Average 2.3 deploys/week (target: daily)
B
Blast Radius
One bad commit takes down everything
No fault isolation between domains
MTTR: 47 min avg (last quarter)
C
Team Coupling
Merge conflicts across unrelated features
Shared DB schema = hidden dependencies
No clear ownership boundaries

## Slide 3
Target Architecture
Clients (Web / Mobile / API Consumers)
▼
API Gateway (routing, auth, rate limiting)
▼
User
Service
Order
Service
Payment
Service
Inventory
Service
▼
Event Bus (Kafka — async communication between services)
Isolated Data Stores (each service owns its data)

## Slide 4
Migration Strategy: Strangler Fig
Incrementally replace monolith capabilities without a big-bang rewrite
01
Identify & Isolate
Map domain boundaries.
Extract shared DB tables.
Define service contracts.
02
Facade Layer
Insert API gateway.
Route traffic to monolith.
Add feature flags.
03
Extract Services
Peel off one service
at a time. Dual-write
for data consistency.
04
Retire Monolith
Redirect all traffic.
Decommission old code.
Clean up shared DB.

## Slide 5
Risk Matrix
Risk | Likelihood | Impact | Mitigation
Data inconsistency during dual-write period | HIGH | HIGH | Event sourcing + reconciliation jobs running every 5 min
Service discovery failures in early rollout | MEDIUM | HIGH | Circuit breakers + fallback to monolith endpoints
Network latency increase from service-to-service calls | HIGH | MEDIUM | Async messaging via Kafka; cache hot paths
Team skill gap on distributed systems | MEDIUM | MEDIUM | Training program + embedded SRE in each squad
Operational complexity (20+ services to manage) | HIGH | LOW | Standardized templates, shared CI/CD pipeline

## Slide 6
6-Month Phased Rollout
Month 1
Foundation
API gateway setup
Service mesh infra
CI/CD templates
Month 2
First Service
Extract User Service
Dual-write migration
Integration tests
Month 3
Expand
Extract Order Service
Event bus (Kafka)
Monitoring baseline
Month 4
Accelerate
Payment + Inventory
Remove dual-writes
Load testing
Month 5
Stabilize
Performance tuning
Chaos engineering
Runbook creation
Month 6
Complete
Monolith retirement
DNS cutover
Retrospective

## Slide 7
Monitoring & Observability
Instrument from day one — you cannot debug what you cannot see
Metrics
Request rate, error rate, duration (RED)
Queue depth & consumer lag
CPU / memory / GC per service
Custom business metrics (orders/sec)
Traces
Distributed tracing (OpenTelemetry)
Trace ID propagation across services
Latency breakdown per hop
Automatic span instrumentation
Logs
Structured JSON logging (no plaintext)
Correlation IDs in every log line
Centralized aggregation (ELK / Loki)
Alert on error rate spikes
Tooling Stack
Prometheus + Grafana
Metrics & dashboards
Jaeger / Tempo
Distributed tracing
ELK Stack / Loki
Log aggregation
PagerDuty
Alerting & on-call
OpenTelemetry SDK
Unified instrumentation

## Slide 8
Team Structure
Organize squads around service boundaries ("You build it, you run it")
User Squad
4 engineers
User Service, Auth, Profiles
Commerce Squad
5 engineers
Order Service, Cart, Checkout
Payments Squad
4 engineers
Payment Service, Billing, Refunds
Inventory Squad
3 engineers
Inventory Service, Warehouse API
Platform Squad
4 engineers
API Gateway, CI/CD, Infra, Observability
Key Principles
Full ownership: build, deploy, operate
On-call rotation per squad
Cross-squad API contract reviews
Weekly architecture sync
Embedded SRE in Platform squad
Shared runbook repository

## Slide 9
Success Metrics
< 200ms
P99 Latency Target
Currently: 450ms
10x/day
Deploy Frequency
Currently: 2.3x/week
< 15min
MTTR Target
Currently: 47 min
Metric | Current | 6-Month Target
Change failure rate | 18% | < 5%
Lead time for changes | 2 weeks | < 1 day
Service availability | 99.5% | 99.95%
Test coverage | 42% | > 80%

## Slide 10
Questions?
Let's build this together.
Alex Chen
alex.chen@company.dev | #platform-migration | Confluence: /microservices