## Slide 1
Migrating from
Monolith to
Microservices
A Practical Guide for Backend Engineering Teams
Alex Chen
Staff Engineer, Platform Team
March 2026
MONOLITH
TRANSITION
MICROSERVICES

## Slide 2
2
The Monolith: Where We Are Today
!
Deployment
Bottleneck
Single deployable artifact means every change requires full regression. Average deploy cycle: 2 weeks. One broken test blocks 20 engineers.
X
Blast
Radius
A memory leak in payments takes down search, checkout, and user profiles. No fault isolation between domains.
~
Team
Coupling
Shared codebase forces coordination overhead. Merge conflicts across teams. Code ownership is unclear.

## Slide 3
3
Target Architecture
API GATEWAY
User
Service
Order
Service
Payment
Service
Search
Service
EVENT BUS (Kafka / RabbitMQ)
PostgreSQL
MongoDB
Redis
Elasticsearch
Clients

## Slide 4
4
Migration Strategy: Strangler Fig Pattern
Incrementally replace monolith capabilities with services, routing traffic progressively.
01
Identify
Boundaries
Map domain contexts.
Define service APIs.
Audit DB dependencies.
02
Build
Proxy Layer
Deploy API gateway.
Route traffic to monolith.
Add observability hooks.
03
Extract
Services
Migrate one domain
at a time. Dual-write
for data consistency.
04
Decommission
Monolith
Remove legacy code.
Consolidate data stores.
Retire old infra.

## Slide 5
5
Risk Matrix
RISK | IMPACT | LIKELIHOOD | MITIGATION
Data inconsistency during dual-write | HIGH | HIGH | Event sourcing + idempotent consumers
Service-to-service latency spikes | MED | HIGH | Circuit breakers + timeout budgets
Distributed tracing gaps | MED | MED | Mandatory trace context propagation
Team skill gaps with new infra | LOW | HIGH | Pairing sessions + runbooks from week 1
Scope creep and gold-plating | MED | MED | Strict phase gates, no re-architecture mid-flight

## Slide 6
6
6-Month Phased Rollout
Month 1
Month 2
Month 3
Month 4
Month 5
Month 6
Discovery &
Boundary Mapping
Discovery & Boundary Mapping
API Gateway &
Proxy Setup
API Gateway & Proxy Setup
Extract User
Service
Extract User Service
Extract Order
Service
Extract Order Service
Extract Payment
Service
Extract Payment Service
Monitoring &
Hardening
Monitoring & Hardening
Gateway Live
50% Traffic Migrated
Monolith Retired

## Slide 7
7
Monitoring & Observability
Instrument from day one. You cannot debug what you cannot see.
T
Distributed Tracing
Jaeger / OpenTelemetry across every service boundary. Mandatory trace-id propagation.
L
Structured Logging
JSON logs with correlation IDs. Ship to centralized ELK stack. Standardize log levels.
M
Metrics & Dashboards
RED metrics (Rate, Errors, Duration) per service. Grafana dashboards per squad.
A
Alerting & SLOs
Define SLOs before launch. Alert on burn rate, not raw thresholds. PagerDuty integration.
H
Health Checks
Liveness + readiness probes. Dependency health checks. Circuit breaker status.
S
Synthetic Monitoring
End-to-end canary tests. Continuously verify critical user journeys in production.

## Slide 8
8
Team Structure: Service-Aligned Squads
BEFORE: Feature Teams
20 engineers in one monolith repo
Cross-team merge conflicts daily
Shared on-call rotation (noisy)
No clear code ownership
Coordination overhead scales O(n^2)
MONOLITH REPO
AFTER: Service Squads
4-5 engineers per squad, owns 1 service
Independent deploy cadence
On-call scoped to own service
Full ownership: build, run, support
Platform team for shared infra
User
Order
Payment
Search

## Slide 9
9
Success Metrics
< 200ms
P99 Latency Target
Per-service, measured at gateway
10x/day
Deploy Frequency
Per service, independent pipelines
< 30min
MTTR Target
Mean time to recovery per incident
Change Failure Rate
< 5%
~18% today
Lead Time for Changes
< 1 day
~2 weeks today
Service Availability
99.95%
99.5% (monolith)
On-Call Alert Noise
-70%
Scoped per service

## Slide 10
10
Questions?
Key Takeaways
Strangler fig lets us migrate incrementally without big-bang risk
Service boundaries follow domain contexts, not technical layers
Observability is not optional -- instrument from day one
Team topology drives architecture; align squads to services
Alex Chen | achen@company.dev | #platform-eng on Slack