## Slide 1
Project Chimera
Monolith Decomposition Plan — VP Engineering Review
340K
Lines of Code
(monolith surface area)
22
Engineers
Delivering on single codebase
$133K
Per Quarter
Estimated CI/deploy friction cost
Strangler Fig Pattern · Phase 1–3 · M1–M6 2026
1 / 6
PROJECT CHIMERA | VP ENGINEERING REVIEW | CONFIDENTIAL

## Slide 2
Current State & Pain Points
DORA metrics reveal systemic delivery constraints — Q1 2026 benchmark
2 / 6
PROJECT CHIMERA | VP ENGINEERING REVIEW | CONFIDENTIAL
DORA METRICS — Q1 2026 BENCHMARK
METRIC
CURRENT
ELITE P50
STATUS
Deploy Frequency
1.8/wk
1/day
LAGGING
Lead Time for Change
12.3 days
1–7 days
LAGGING
Change Failure Rate
18.2%
<15%
FAILING
Mean Time to Recover
4.2 hrs
<1 hr
LAGGING
Build Time (CI)
47 min
<15 min
FAILING
6.8% CI flakiness = 'retry and pray' culture
Teams spend 9 min avg per failed pipeline waiting for reruns
COST IMPACT ANALYSIS
$133K
Quarterly Engineering Waste
1,400 eng-hrs / qtr
× $95 / hr (blended rate)
= $133,000 quarterly
friction cost
= $532,000 annualized
opportunity cost
Source: Engineering time-tracking Q4 2025, 22-engineer base

## Slide 3
Target Architecture & Service Boundaries
Six bounded-context services — Strangler Fig extraction sequence
3 / 6
PROJECT CHIMERA | VP ENGINEERING REVIEW | CONFIDENTIAL
SERVICE BOUNDARY DEFINITIONS
SERVICE
SQUAD
DATABASE
API STYLE
PRIORITY
User Service
Identity
PostgreSQL
REST + gRPC
P0
Order Service
Commerce
PostgreSQL
REST
P1
Payment Service
Commerce
PostgreSQL
REST + Events
P0
Search Service
Discovery
Elasticsearch
REST
P1
Notification Svc
Platform
Redis + PG
Events
P2
Analytics Service
Data
ClickHouse
gRPC
P2
KEY ARCHITECTURAL DECISIONS
· API Gateway: Kong (rate limiting, auth offload, canary routing)
· Service Mesh: Istio (mTLS, circuit breakers, traffic shaping, observability)
· Event Bus: Kafka 3-broker cluster (ordered delivery, at-least-once, compacted topics per service)
· Data Isolation: Each service owns its schema — no cross-service DB joins; CDC via Debezium for sync

## Slide 4
ARCHITECTURE DECISION RECORD
Why Strangler Fig?
✗ REJECTED
Full Rewrite
· 14–18 months estimated
· Dedicated team of 8
· Feature freeze required
· Zero revenue delivery during migration
"Netscape, Basecamp: 2–3× longer than estimated. Risk of losing product-market fit mid-rewrite."
− INSUFFICIENT
Modularize Monolith
· Enforced module boundaries only
· Atlas Modular Q4 2025: -30% conflicts
· Deploy frequency: unchanged
· DB coupling problem persists
"Boundary violations drop but deployment bottleneck remains. One bad migration still blocks all teams."
✓ SELECTED
Strangler Fig
· Incremental, bounded-risk extraction
· Revenue delivery continues throughout
· Proven: User Service Q1 2026
· 3 weeks, zero incidents
"Validated internal proof-of-concept. Monolith stays runnable as safety net throughout migration."
Scope: Reporting + Admin modules remain in monolith. Goal is deployment velocity — not zero-monolith.
Timeline confidence: 65% Phase 1–2 · 40% Phase 3 (ClickHouse learning curve factored in)
4 / 6
PROJECT CHIMERA | VP ENGINEERING REVIEW | CONFIDENTIAL

## Slide 5
Migration Roadmap
Strangler Fig extraction — M1–M6 2026 · Three-phase delivery
5 / 6
PROJECT CHIMERA | VP ENGINEERING REVIEW | CONFIDENTIAL
Phase 1: Foundation
Months 1–2
Phase 2: Commerce Core
Months 3–4
Phase 3: Platform
Months 5–6
TASK
TYPE
RISK
API Gateway (Kong)
Setup
LOW
OTel Instrumentation
Observability
LOW
User Service Extract
Core P0
MEDIUM
Kafka Cluster Provision
Infra
MEDIUM
DB Migration Tooling
Flyway+CDC
LOW
TASK
TYPE
RISK
Order Service Extract
Commerce P1
HIGH
Payment Service Extract
Commerce P0
CRITICAL
Checkout Saga Pattern
Resilience
HIGH
Search Extraction
Discovery P1
MEDIUM
TASK
TYPE
RISK
Notification Service
Platform P2
MEDIUM
Analytics (ClickHouse)
Data P2
HIGH
Monolith Decommission
Cleanup
MEDIUM
Chaos Engineering
Resilience
LOW
Gate criteria: Each phase requires >95% test coverage on extracted service, P95 latency <150ms, and zero SEV-1 incidents for 5 business days before proceeding.

## Slide 6
Risk Matrix & Success Metrics
Six identified risks · Eight before/after delivery targets at 12 months
6 / 6
PROJECT CHIMERA | VP ENGINEERING REVIEW | CONFIDENTIAL
RISK REGISTER
RISK
SEV
MITIGATION
Saga transaction failures
CRITICAL
Compensation logic + monolith fallback flag
Kafka instability
HIGH
Confluent Cloud managed + specialist hire Q1
Data inconsistency
HIGH
CDC Debezium + nightly reconciliation jobs
Service latency increase
MEDIUM
200ms budget enforcement, Istio circuit breakers
Team cognitive load
MEDIUM
Phased tooling adoption, inner-source docs
PCI compliance scope creep
MEDIUM
Security review M2; Stripe hosted checkout
12-MONTH TARGETS
METRIC
NOW
TARGET
Deploy Frequency
1.8/wk
1+/day
Lead Time
12.3d
<2d
Change Failure Rate
18.2%
<8%
MTTR
4.2 hrs
<30 min
P99 API Latency
820ms
<200ms
Build Time (CI)
47 min
<8 min
CI Flakiness
6.8%
<1%
Dev Satisfaction
5.8/10
8.0/10