## Slide 1
Project Chimera: Monolith Decomposition Plan
Presented to VP Engineering | April 2026
340K
Lines of Code
2,800
DB Tables
22
Backend Engineers
$133K/qtr
Wasted Engineering Cost
DORA METRICS — CURRENT STATE
Metric | Current | Industry P50 | Gap
Deploy frequency | 1.8/wk | 1/day–1/wk | Bottom of "medium"
Lead time | 12.3 days | 1–7 days | 2× over ceiling
Change failure rate | 18.2% | 0–15% | Above threshold
MTTR | 4.2 hours | <1 hr – <1 day | Functional but slow
Build time | 47 min | — | Devs context-switch
Project Chimera — Monolith Decomposition Plan
1 / 6

## Slide 2
Target Architecture: Strangler Fig Pattern
SERVICE BOUNDARIES
Service | Owner Squad | Database | API Style | Priority
User Service | Identity | PostgreSQL | REST + gRPC | P0
Order Service | Commerce | PostgreSQL | REST + Events | P0
Payment Service | Commerce | PostgreSQL + Stripe | REST | P1
Search Service | Discovery | Elasticsearch 8 | REST | P1
Notification Service | Platform | PostgreSQL + SQS | Async | P2
Analytics Service | Data | ClickHouse | gRPC | P2
ARCHITECTURE FLOW
API Gateway
→
Service Mesh (Istio)
→
6 Microservices
→
Kafka
→
Isolated Data Stores
Key Decisions: Kong/AWS ALB for gateway | Istio service mesh | Kafka 3-broker cluster
Project Chimera — Monolith Decomposition Plan
2 / 6

## Slide 3
ADR: Why Strangler Fig, Not Rewrite
REJECTED
Full Rewrite
14–18 months, 8 engineers, parallel systems risk.
"Basecamp, Netscape — rewrites 2–3× slower than estimated."
INSUFFICIENT
Modularize Only
Tried Q4 2025. Merge conflicts −30% but deploy frequency unchanged. Still one artifact.
SELECTED
Strangler Fig
Incremental, bounded risk. Already proven: User Service extraction Q1 2026 in 3 weeks, zero customer incidents.
SCOPE DECISIONS
Reporting + Admin stay in monolith — low-traffic, low-change, extraction cost > benefit
Timeline confidence: 65% confident Phase 1–2 on time | 40% confident Phase 3 — ClickHouse learning curve
Project Chimera — Monolith Decomposition Plan
3 / 6

## Slide 4
6-Month Phased Migration
Phase 1 — M1-2
Phase 2 — M3-4
Phase 3 — M5-6
Phase 1: Foundation
Task | Owner | Risk
API Gateway setup | Platform | Med
OpenTelemetry rollout | SRE | Low
User Svc extraction | Identity | Med
Kafka cluster | SRE | High
DB migration tooling | Data | Med
Phase 2: Core Services
Task | Owner | Risk
Order Service | Commerce | High
Payment Service | Commerce | High
Saga pattern | Commerce | High
Search Service | Discovery | Med
— | — | —
Phase 3: Completion
Task | Owner | Risk
Notification Svc | Platform | Med
Analytics Svc | Data | High
Decommission modules | SRE | Med
Chaos engineering | SRE | Med
— | — | —
Project Chimera — Monolith Decomposition Plan
4 / 6

## Slide 5
Risk Matrix & Monitoring Stack
RISK MATRIX
Risk | Like. | Impact | Sev. | Mitigation
Saga failures | HIGH | HIGH | CRITICAL | Compensation + feature flag
Kafka instability | MEDIUM | HIGH | HIGH | Confluent Cloud + specialist
Data inconsist. | HIGH | MEDIUM | HIGH | Debezium CDC + hourly recon
Service latency | MEDIUM | MEDIUM | MEDIUM | 200ms budget + circuit break
Team overload | MEDIUM | MEDIUM | MEDIUM | Phased tools + office hours
PCI scope | LOW | HIGH | MEDIUM | Sec review M2 + Stripe
OBSERVABILITY STACK
Layer | Tool | Coverage | Alert Threshold
Metrics | Prometheus + Grafana | RED metrics | Error >1% / 5min
Tracing | Jaeger + OTEL | End-to-end flow | Trace >2s
Logging | ELK Stack | Structured JSON | Error >50/min
Health | K8s probes | Svc availability | 3 fail → page
Synthetic | Datadog | Critical flows | Any fail → page
Project Chimera — Monolith Decomposition Plan
5 / 6

## Slide 6
Success Metrics & Squad Structure
BEFORE / AFTER TARGETS
Metric | Current | 6-Month | 12-Month
Deploy frequency | 1.8/wk | 3/wk/svc | 1+/day/svc
Lead time | 12.3 days | 5 days | <2 days
Change failure rate | 18.2% | 12% | <8%
MTTR | 4.2 hrs | 1.5 hrs | <30 min
P99 API latency | 820ms | 400ms | <200ms
Build time | 47 min | 15 min | <8 min
Test flakiness | 6.8% | 3% | <1%
Dev satisfaction | 5.8/10 | 7.0/10 | 8.0/10
SQUAD OWNERSHIP
Squad | Services | Size | On-Call
Identity | User, Auth | 4 | Yes
Commerce | Order, Payment | 6 | Yes
Discovery | Search | 3 | Shared
Platform | Notifications, GW | 4 | Yes
Data | Analytics | 3 | Shared
SRE | Kafka, K8s, Monitor | 3 | Yes (primary)
SRE squad is primary on-call for all infrastructure. Service squads escalate Kafka/K8s issues to SRE first.
Project Chimera — Monolith Decomposition Plan
6 / 6