## Slide 1
PROJECT CHIMERA
Monolith
Decomposition
Plan
Atlas: 340K LOC | 14 Django Apps | 2,800 Tables | 22 Engineers
340K
LOC
Python 3.11
2,800
DB Tables
PostgreSQL 15
22
Engineers
4 squads
$133K
Quarterly Waste
~1,400 eng-hrs
DORA METRICS & PAIN POINTS
Metric | Current | Industry P50 | Gap / Impact
Deploy frequency | 1.8/week | 1/day - 1/week | Bottom of medium
Lead time (commit to prod) | 12.3 days | 1 day - 1 week | 2x over ceiling
Change failure rate | 18.2% | 0 - 15% | Above threshold
MTTR | 4.2 hours | < 1 hour - 1 day | Functional but slow
CI build time | 47 min | -- | Context-switch tax
Merge conflicts/week | 3.2 avg (peak 8) | -- | Cross-team coordination
Rollback rate | 1 in 5.5 deploys | -- | Low release confidence
Test flakiness | 6.8% CI runs | -- | Retry-and-pray culture

## Slide 2
Target Architecture
Strangler Fig | API Gateway | Event-Driven | Service per Domain
SERVICE BOUNDARIES
Service | Squad | DB | API | Priority
User Service | Identity | PostgreSQL | REST + gRPC | P0
Order Service | Commerce | PostgreSQL | REST + events | P0
Payment Service | Commerce | PG + Stripe | REST (sync) | P1
Search Service | Discovery | Elasticsearch | REST | P1
Notification Svc | Platform | PG + SQS | Async events | P2
Analytics Svc | Data | ClickHouse | gRPC internal | P2
ARCHITECTURE
API Gateway (Kong)
User
Order
Payment
Search
Notif.
Analytics
Event Bus (Kafka)
PostgreSQL x4 | ES | ClickHouse | Redis
KEY DECISIONS
Database-per-service
No shared tables. Each service owns its data. Cross-service queries via events or API calls.
Event-driven async
Kafka for inter-service communication. Sync REST only for user-facing checkout flow.
Strangler Fig pattern
Incremental extraction behind API gateway. Monolith stays live. Rollback = route back to monolith.
2

## Slide 3
Architecture Decision Record
Why Strangler Fig, Not Rewrite, Not Modularize
FULL REWRITE
REJECTED
Estimated 14-18 months with 8 engineers (Go + gRPC greenfield)
Dual-system maintenance: monolith + new system in parallel
340K lines of tested business logic must be re-discovered
Industry data: rewrites take 2-3x longer than estimated
Netscape, Basecamp case studies show high failure rate
MODULARIZE MONOLITH
INSUFFICIENT
Tried Q4 2025: 6 weeks extracting Django apps into packages
Merge conflicts dropped 30% but deploy frequency unchanged
47-min CI build didn't improve; blast radius didn't shrink
Addresses code organization, not deployment coupling
Deployment coupling is the actual bottleneck
STRANGLER FIG
SELECTED
Incremental extraction: ship value while de-risking
Each service validated in prod alongside monolith before cutover
If extraction fails, route traffic back to monolith instantly
Q1 2026 prototype: User Service extracted in 3 weeks, zero incidents
Risk bounded to one service at a time, not entire system
SCOPE & TIMELINE CONFIDENCE
Decision | Detail | Confidence
Extracting (6 services) | User, Order, Payment, Search, Notification, Analytics | Phase 1-2: 65% ¦ Phase 3: 40%
NOT extracting | Reporting, Admin, Billing (low-traffic, low-change; cost > benefit) | Stay in monolith indefinitely
Timeline risk | Phase 3 depends on ClickHouse adoption (unknown learning curve). Padded 2 weeks. | 40% on-time for Phase 3
3

## Slide 4
6-Month Migration Plan
Phase 1: Foundation (M1-M2)
Phase 2: Commerce Core (M3-M4)
Phase 3: Platform & Optimize (M5-M6)
PHASE 1: FOUNDATION (MONTH 1-2)
Task | Owner | Risk
Deploy API Gateway (Kong) | SRE | SPOF - need HA
Instrument w/ OpenTelemetry | SRE + all | ~2-3% overhead
Extract User Service | Identity | Session migration
Set up Kafka (3 brokers) | SRE | No Kafka exp.
DB migration tooling | DBA | Data consistency
PHASE 2: COMMERCE CORE (MONTH 3-4)
Task | Owner | Risk
Extract Order Service | Commerce | 47 cross-imports
Extract Payment Service | Commerce | PCI scope change
Implement checkout saga | Comm+Ident | Complex failures
Search Service extraction | Discovery | 4hr reindex
PHASE 3: PLATFORM & OPTIMIZATION (MONTH 5-6)
Task | Owner | Risk
Notification Service | Platform | Low risk
Analytics Service | Data | 18mo data migration
Decommission monolith modules | All squads | Residual coupling
Perf tuning + chaos eng. | SRE | Unknown unknowns
CRITICAL PATH & DEPENDENCIES
1. API Gateway must be live before any extraction
Gateway routes traffic; services are useless without it.
2. User Service extracted before Order Service
Orders depend on user identity. Extract dependency first.
3. Kafka operational before Commerce extractions
Order + Payment services communicate via events.
4. Checkout saga requires Order + Payment + User
All three services must be stable before saga goes live.
5. Monolith fallback active until Phase 3 complete
Feature flag per service; route back on failure.
4

## Slide 5
Risk Matrix & Observability Stack
RISK MATRIX
Risk | L | I | Sev. | Mitigation
Distributed txn failures (checkout saga) | H | H | CRITICAL | Compensation/rollback per saga step; feature flag fallback to monolith
Kafka instability (team inexperience) | M | H | HIGH | Hire Kafka specialist 3mo; use Confluent Cloud managed; start with 3 topics
Data inconsistency (dual-write migration) | H | M | HIGH | CDC with Debezium (not app-level dual-write); hourly reconciliation jobs
Service latency exceeds budget | M | M | MEDIUM | P99 budget 200ms/call; Istio circuit breakers 500ms timeout; async-first
Team cognitive overload (new tools) | M | M | MEDIUM | Phase tool adoption: Kafka M1, Istio M3, ClickHouse M5; weekly arch hours
PCI scope expansion (Payment Svc) | L | H | MEDIUM | Security review M2; use Stripe hosted checkout; document compliance bounds
MONITORING & OBSERVABILITY STACK
Layer | Tool | Coverage | Alert Threshold
Metrics | Prometheus + Grafana | RED: rate, error, duration; saturation | Err > 1% (5m) ¦ P99 > 500ms (10m)
Tracing | Jaeger + OpenTelemetry | End-to-end request flow across services | Trace > 2s ¦ Span errors > 5%
Logging | ELK Stack | Structured JSON; correlation IDs | Error rate > 50/min per service
Health | K8s probes | Liveness + readiness; dependency health | Probe fail = restart; 3x = page SRE
Synthetic | Datadog Synthetics | Login, search, checkout, payment flows | Any failure = immediate page
Alerting | PagerDuty | P1 page ¦ P2 Slack ¦ P3 next biz day | Tiered escalation
Key Grafana Dashboards: Service Overview (RED per svc) | Kafka Health (consumer lag, replication) | Checkout Saga (success rate, step failures) | Deploy Tracker (canary, rollbacks)
5

## Slide 6
Success Metrics & Team Ownership
BEFORE / AFTER TARGETS
Metric | Current | 6-Month Target | 12-Month Target | Measurement
Deploy frequency | 1.8/week | 3/week per svc | 1+/day per svc | CI/CD pipeline
Lead time | 12.3 days | 5 days | < 2 days | PR merge to deploy
Change failure rate | 18.2% | 12% | < 8% | Hotfix / total deploys
MTTR | 4.2 hours | 1.5 hours | < 30 min | PagerDuty incidents
P99 API latency | 820ms | 400ms | < 200ms | Prometheus histograms
CI build time | 47 min | 15 min/svc | < 8 min | GitHub Actions
Test flakiness | 6.8% | 3% | < 1% | CI failure rate
Dev satisfaction | 5.8/10 | 7.0/10 | 8.0/10 | Quarterly survey
TARGET TEAM STRUCTURE: YOU BUILD IT, YOU RUN IT
Squad | Services Owned | Size | On-Call
Identity | User Service, Auth | 4 eng | Own pager
Commerce | Order Service, Payment Service | 6 eng | Own pager
Discovery | Search Service | 3 eng | Shared w/ Platform
Platform | Notification Svc, API Gateway, shared libs | 4 eng | Own pager
Data | Analytics Service | 3 eng | Shared w/ Platform
SRE | Kafka, Kubernetes, monitoring, incident response | 3 eng | Primary escalation
Principle: Each squad owns their service SLOs, deploys independently, and carries their own pager. SRE provides platform, not babysitting. Coordination overhead drops from O(n²) to O(n).
6