## Slide 1
Project Chimera
Monolith Decomposition Plan · Atlas → Microservices · VP Engineering + 20 Backend Engineers · March 2026
340K
Lines of Python
2,800
DB Tables (single PG)
14
Django Apps
22
Backend Engineers
DORA Metrics vs. Industry P50 — Measured, Not Anecdotal
Metric | Current (Atlas) | DORA Industry P50 | Status
Deploy Frequency | 1.8 / week (every 3.9 days) | 1/day – 1/week | Bottom of 'Medium'
Lead Time (commit → prod) | 12.3 days | 1 day – 1 week | 2× over Medium ceiling
Change Failure Rate | 18.2% | 0 – 15% | Above Medium threshold
Mean Time to Recover | 4.2 hours | < 1 hr – < 1 day | Functional but slow
CI Build Time | 47 min (full suite) | — | Forced context-switching
Cost of Friction: ~1,400 engineer-hours / quarter → ~$133K / quarter wasted
Breakdown: deployment delays + conflict resolution + rollback recovery + flaky-test investigation @ $95 / hr loaded cost

## Slide 2
Target Architecture — Strangler Fig Decomposition
Domain-driven service boundaries · Kong API Gateway · Istio Service Mesh · Kafka · Isolated data store per service
Service | Owner | Data Store | API | Priority
User Service | Identity | PostgreSQL (isolated) | REST + gRPC | P0 — 1st Extract
Order Service | Commerce | PostgreSQL (isolated) | REST + Events | P0 — High Coupling
Payment Service | Commerce | PostgreSQL + Stripe | REST (sync) | P1 — After Orders
Search Service | Discovery | Elasticsearch 8 | REST | P1 — Low Coupling
Notification Svc | Platform | PostgreSQL + SQS | Async/Events | P2 — Low Risk
Analytics Service | Data | ClickHouse | gRPC (int.) | P2 — Read-Only
Strangler Fig:
Incremental extraction behind gateway — not a big-bang rewrite.
DB Isolation:
Each service owns its schema — no shared tables, no cross-service joins.
Async-first:
Kafka events for consistency; sync only on checkout-critical paths.
You build it:
Each squad owns SLOs, deploys independently, carries their own pager.
Bounded scope:
Reporting & Admin stay in monolith — goal is friction removal, not purity.
TARGET ARCHITECTURE
Clients (Web · Mobile · API)
API Gateway
Kong · Rate Limit · Auth · Circuit Breaker
SERVICE MESH (Istio)
User
Service
Order
Service
Payment
Service
Event Bus (Kafka)
Topics: user.* · order.* · payment.*
Search
Service
Notif.
Service
Analytics
Service
Isolated Data Stores
PostgreSQL×4 · Elasticsearch · ClickHouse · Redis/svc

## Slide 3
Architecture Decision Record — Why Strangler Fig, Not Rewrite
2-week evaluation spike · April 14–25, 2026 · Three options scored against risk, timeline, and reversibility
Option 1: Full Rewrite
Greenfield rebuild in Go + gRPC
Est. 14–18 months, 8 dedicated engineers
Monolith still needs maintenance concurrently
Two systems running in parallel for 12+ months
Industry data: rewrites take 2–3× est. timeline
Netscape, Basecamp: frequently fail to ship
340K lines of tested logic — all edge cases must
be rediscovered the hard way during rewrite
REJECTED
Option 2: Modularize Monolith
Tried Q4 2025 as 'Atlas Modular' initiative
6 weeks: Django apps → discrete packages
Merge conflicts ↓30% — deploy freq. unchanged
Still one artifact → 47-min CI build unchanged
Blast radius unchanged — one deploy breaks all
Addresses code coupling, not deploy coupling
Root cause is artifact cohesion, not structure
No path to independent deploys without extraction
REJECTED
Option 3: Strangler Fig
Incremental extraction behind API Gateway
Each service validated in prod before cutover
Rollback = reroute traffic back to monolith
Risk bounded to one service at a time
Proven in Q1 2026 prototype:
User Svc: 3 wks extract, 2 wks parallel run
Cutover with zero customer-facing incidents
Scales to harder extractions (Orders, Payments)
CHOSEN
SCOPE BOUNDARIES & TIMELINE CONFIDENCE
What We Are NOT Doing
• Reporting & Admin stay in monolith; low-traffic, low-change — extraction cost > benefit
• Not self-hosting Kafka — Confluent Cloud managed; team has zero Kafka experience
• Istio deferred to Month 3; ClickHouse to Month 5 — stagger tools to avoid overload
Timeline Confidence
• 65% confident: Phase 1–2 on schedule — validated by Q1 2026 User Service prototype
• 40% confident: Phase 3 on time — ClickHouse adoption has unknown learning curve
• Checkout Saga is highest-risk item; may slip Phase 2 by 1 week — flagged proactively

## Slide 4
Migration Plan — 6-Month Phased Rollout
Phase 1: Foundation (M1–2) · Phase 2: Commerce Core (M3–4) · Phase 3: Platform & Optimization (M5–6)
Phase 1: Foundation · Months 1–2
Phase 2: Commerce Core · Months 3–4
Phase 3: Platform & Opt. · Months 5–6
Phase 1: Foundation
Task | Owner | Deliverable
Deploy API Gateway (Kong) | SRE | All traffic via gateway; monolith = upstream
Instrument with OpenTelemetry | SRE + all squads | Distributed tracing: HTTP + Celery tasks
Extract User Service | Identity squad | User CRUD, auth, permissions standalone
Stand up Kafka (3 brokers) | SRE | Event bus; user.created / user.updated topics
DB migration tooling (CDC) | DBA | Debezium CDC; dual-write; reconciliation jobs
Phase 2: Commerce Core
Task | Owner | Deliverable
Extract Order Service | Commerce squad | Orders, carts, pricing standalone; Kafka consumer
Extract Payment Service | Commerce squad | Stripe, invoicing, refunds standalone
Implement Checkout Saga | Commerce + Identity | Distributed txn: order → inventory → charge
Extract Search Service | Discovery squad | Elasticsearch standalone; monolith → Kafka producer
Phase 3: Platform & Optimization
Task | Owner | Deliverable
Extract Notification Service | Platform squad | Email/SMS/push via SQS; template management
Extract Analytics Service | Data squad | ClickHouse ingestion; dashboards migrate to new APIs
Decommission monolith modules | All squads | Remove extracted code; monolith = thin orchestrator
Chaos engineering + perf tuning | SRE | Latency targets met; circuit breakers tested; runbooks

## Slide 5
Risk Matrix & Observability Stack
Severity-coded risks with bounded mitigations · Full-stack monitoring instrumented from Phase 1
Risk Matrix
Risk | Likelihood | Impact | Severity | Mitigation
Distributed transaction failures (checkout saga) | HIGH | HIGH | CRITICAL | Compensation/rollback per saga step; feature flag → monolith checkout fallback; integration tests
Kafka instability (team inexperience) | MEDIUM | HIGH | HIGH | Hire Kafka specialist 3 months; Confluent Cloud managed; start with 3 low-throughput topics
Data inconsistency during dual-write | HIGH | MEDIUM | HIGH | Debezium CDC instead of app dual-write; hourly reconciliation jobs; rollback documented
Service-to-service latency overrun | MEDIUM | MEDIUM | MEDIUM | P99 200ms budget per hop; Istio circuit breakers 500ms; async events over sync calls
PCI scope expansion (Payment Service) | LOW | HIGH | MEDIUM | Security review M2 before extraction; Stripe hosted checkout minimises PCI surface
Observability Stack
Layer | Tool | Coverage | Alert Threshold
Metrics | Prometheus + Grafana | RED (rate, errors, duration); saturation (CPU, mem, conns) | Error rate >1% / 5 min · P99 >500ms / 10 min
Tracing | Jaeger + OpenTelemetry | End-to-end request flow; latency per service hop | Trace >2 s · Span error rate >5%
Logging | ELK Stack | Structured JSON logs; correlation IDs across services | Error log rate >50 / min per service
Health Checks | K8s liveness + readiness | Service availability; DB / Redis / Kafka health | Probe failure → restart; 3× → page SRE
Alerting | PagerDuty | Tiered: P1 page → P2 Slack → P3 next business day | Per thresholds above
Key Grafana Dashboards: Service Overview (RED per service) · Kafka Health (consumer lag, broker disk, replication) · Checkout Saga (success %, avg duration, failure by step) · Deploy Tracker (last deploy, canary %, rollback count)

## Slide 6
Success Metrics & Target Team Structure
Before/after DORA targets · 6-month and 12-month checkpoints · Squad ownership · You build it, you run it
Before / After — DORA & Engineering Health Targets
Metric | Current (Atlas) | 12-Month Target | Measurement
Deploy Frequency | 1.8 / week | 1+ / day per service | CI/CD pipeline metrics
Lead Time (→ prod) | 12.3 days | < 2 days | PR merge → deploy timestamp
Change Failure Rate | 18.2% | < 8% | Hotfix deploys / total
MTTR | 4.2 hours | < 30 minutes | PagerDuty incident duration
P99 API Latency | 820 ms | < 200 ms | Prometheus histograms
CI Build Time | 47 minutes | < 8 min / service | GitHub Actions duration
Test Flakiness | 6.8% | < 1% | CI failure rate (excl. bugs)
Dev Satisfaction | 5.8 / 10 | 8.0 / 10 | Quarterly eng survey
Current — problem state
12-Month Target
Target Squad Structure — Service Ownership Model
Squad | Services Owned | Size | On-Call | Key Responsibility
Identity | User Service, Auth | 4 eng | Yes — own pager | User CRUD, org mgmt, JWT / SSO
Commerce | Order Service, Payment Service | 6 eng | Yes — own pager | Checkout saga, Stripe, invoicing, pricing
Discovery | Search Service | 3 eng | Shared w/ Platform | Elasticsearch, product index, query logs
Platform | Notif. Svc, API Gateway, shared libs | 4 eng | Yes — own pager | SQS templates, Kong routing, dev tooling
Data | Analytics Service | 3 eng | Shared w/ Platform | ClickHouse, Kafka consumers, metrics
SRE | Kafka, K8s, monitoring, incidents | 3 eng | Yes — primary escalation | Platform reliability, chaos eng., runbooks